## Slide 1
Card Conformance Tool (CCT)
Project Kickoff Meeting
Date: 25 October 2017
Notes: Each deck must include a cover slide.

## Slide 2: Overview
“In order to validate that commercially available PIV and PIV-Interoperable smart cards comply sufficiently with the current relevant standards, the testing program needs a test tool that can safely test a variety of cards on a variety of platforms. “
The scope of the CCT project, the deliverables and the time frames will be presented. In shaping the coming development cycles, all questions and recommendations are welcome.

## Slide 3: Scope - Platform
The CCT will run on the following platforms when an appropriate Java Runtime Environment (JRE) is installed:
Mac OS X 10.11 or later
Windows 10 or later
Red Hat Enterprise Linux 6 or later
Ubuntu LTS release 16.04 or later
Note that on non-Windows platforms, a Personal Computer/Smart Card integration system (such as the MUSCLE PCSC-lite subsystem for Linux or Mac OS X Smart Card Services) must be installed in order for applications (including the CCT) to communicate with smart cards.

## Slide 4: Scope - Testing
The CCT will endeavor to test all selected requirements of the current PIV data model. To the extent possible, the CCT will be “read-only” with respect to the cards under test. That is, no application commands (APDUs) that attempt to alter data on the card will be executed. Test requirements will be drawn from the following standards:
ISO/IEC 7816
ISO/IEC 14443
FIPS 201-2
NIST SP 800-73-4
NIST SP 800-76-2
NIST SP 800-78-4
NIST SP 800-85B
The following will be specifically excluded from the scope of the test suites delivered with the initial version of the CCT:
Secure messaging
Virtual contact interface
On-card comparison operations
Key generation
Card personalization
Card administration

## Slide 5: Scope – Test Interfaces
The CCT will expose both a graphical and a command line interface for executing test cases. The graphical interface will support the following functions:
      Test case selection
      Test configuration
      Test execution
      Progress monitoring
      Log display
      Log filtering
      Log export
      Export of test selection/configuration
      Test case selection filtering (e.g. select only passing cases or only failing cases after an initial run)
The command line interface will be primarily configured using files exported from the graphical interface. It will offer options for selecting configuration files and for selecting which reader should be used for test execution. It will offer an interactive display of test progress along with the same log file output as the graphical tool.

## Slide 6: Scope – Tool Releases
All test tools will be published to GitHub under a mutually agreeable OSI-approved open source license which is compatible with the components required to build them. Currently this is anticipated to be a variant of the 2-clause (“simplified”) BSD license. Final selection of dependent components will influence the final license selection.
All user-facing documentation will be published under a mutually agreeable Creative Commons regime to the same repository. (Recommend CC-BY 2.0.)

## Slide 7: Scope – Anticipated Parts List
GUI Toolkit: Eclipse Rich Client Platform 4.x
JUnit
Apache Commons BCEL 6.0
Apache BeanUtils 1.9
Apache Commons CLI 1.4
Apache Commons Codec 1.10
Simple Logging Façade for Java (SLF4J) 1.7
Java Development Kit 8.x
Java Runtime Environment 8.x
Log4j 2.x
Javax.smartcardio API family
Apache Commons I/O 2.5
Bouncy Castle for Java 1.57
Apache Maven 3.3
Apache ant 1.10 (to support oracle self contained application packaging)
Eclipse SWT

## Slide 8: Developmental Tasks
Task | Person -Days
Identify and document test cases & execution requirements | 7
High Level Design | 3
Build/Packaging System Setup | 3
Git Setup/Project Setup | 1
Library Research | 5
Notional Skeletal GUI | 5
Command Line Skeleton | 1
Test Case API Definition | 2
Test Case Development | 90
Progress GUI | 10
Log Filtering/Display GUI | 10
Test Export | 1
Command Line Runner | 3
Log Export | 2
User Guide | 5
API Doc Cleanup | 5
QA Testing | 10

## Slide 9: Schedule

## Slide 10: Deliverables
Test Description Document : Describes test cases to be developed, traces them back to the relevant standards.
Binary Builds : Release builds for Mac OS X, Linux and Windows 10 that are ready to be installed and used by labs, agencies and/or vendors.
User Guide : Documentation for PTH operation from binary builds.
Source Release : Pushed to GSA GitHub repository and tagged with a release identifier.
Build Instructions Document : Describe how to build a new release from GitHub sources.
High Level Design Document : Provides a description of the source tree, all packages used, required dependencies and their purpose, and application design. Provides an overview of patterns used in the APIs.
API Documentation : Automatically generated from annotations in source code. Provides details of how to use and extend APIs within the tool, for example, to develop new tests.

## Slide 11: Items To Be Confirmed
Predecessor activities for Systems Access, Questions, etc
Any Scope Modifications
Flush out Risk Elements to Project for mitigation
Project Progress Meeting Schedule/Cadence
Estimated dates for Milestones and/or Deliverables
All others

## Slide 12
Questions, Answers and Closing Comments